## TaskTime
WBS Task Code | Task Name |  | Optimistic(Hours) | Realistic(Hours) | Pesimistic(Hours)
| Preliminary Work |  | 10 | 19 | 28
PW1 | Database Desing |  | 5 | 10 | 15
PW2 | Team Introduction |  | 1 | 2 | 3
PW3 | Architectural Design |  | 1 | 2 | 3
PW4 | Techincal Documentation |  | 1 | 2 | 3
PW5 | UI Desing |  | 2 | 3 | 4
| FrontEnd Tasks |  | 26 | 40 | 64
FE1 | FE1:Register Page |  | 3 | 5 | 8
FE2 | FE2: Login Page |  | 2 | 3 | 5
FE3 | FE3: Home Page |  | 3 | 5 | 8
FE4 | FE4: Software List Page |  | 1 | 2 | 3
FE5 | FE5: Software Usability Page |  | 4 | 5 | 8
FE6 | FE6: Usability Problem SubmissionPage |  | 3 | 5 | 8
FE7 | FE7: Admin Panel |  | 3 | 5 | 8
FE8 | FE8: Blog Page |  | 3 | 5 | 8
FE9 | FE9: Software Owner Registartion Page |  | 4 | 5 | 8
| BackEnd Tasks |  | 33 | 45 | 65
BE1 | BE1:Register Page Integration |  | 4 | 5 | 8
BE2 | BE2: Login Page Integration |  | 4 | 6 | 8
BE3 | BE3: List Page Integ. |  | 4 | 5 | 8
BE4 | BE4: Usabilit Page Comment Intg. |  | 4 | 6 | 8
BE5 | BE5: Admin Page Authent. |  | 4 | 5 | 8
BE6 | BE6: Blog Page Integ. |  | 4 | 6 | 8
BE7 | BE7: Software Owner Integ. |  | 4 | 5 | 8
BE8 | BE8: E-mail Notrifies Integ. |  | 4 | 6 | 8
BE9 | BE9: Error Handling |  | 1 | 2 | 3
| System Tasks |  | 9 | 17 | 24
S1 | Server Settings |  | 2 | 3 | 5
S2 | Deployment |  | 2 | 4 | 6
S3 | Data Base Integration |  | 5 | 10 | 13
| Total Work |  | 78 | 119 | 176
ND1 | Project Management | 0,2 | 15.6 | 23.8 | 35.2
ND2 | Team Lead (TL) | 0,2 | 15.6 | 23.8 | 35.2
ND3 | Non-Dev Activities | 0,05 | 3.9 | 5.9 | 8.8
ND4 | Planning | 0,1 | 7.8 | 11.9 | 17.6
ND5 | Functional Testing | 0,2 | 15.6 | 23.8 | 35.2
ND6 | Regression Testing | 0,2 | 15.6 | 23.8 | 35.2
ND7 | Performance Testing | 0,01 | 0.78 | 1.19 | 1.76
ND8 | Security Testing | 0,01 | 0.78 | 1.19 | 1.76
ND9 | Bug Fix | 0,25 | 19.5 | 29.75 | 44
| Grand Total |  | 173.16 | 264.13 | 390.72

## Task_Dependencies
Work Package | WBS Task Code | Task Name | Dependency
Preliminary Work
Preliminary Work | PW1 | Database Desing | -
Preliminary Work | PW2 | Team Introduction | PW1
Preliminary Work | PW3 | Architectural Design | PW1
Preliminary Work | PW4 | Techincal Documentation | PW1
Preliminary Work | PW5 | UI Desing | PW1
FrontEnd Tasks
Frond End Tasks | FE1 | FE1:Register Page | PW5,PW2
Frond End Tasks | FE2 | FE2: Login Page | FE1,PW2
Frond End Tasks | FE3 | FE3: Home Page | FE2,PW2
Frond End Tasks | FE4 | FE4: Software List Page | FE3,PW2
Frond End Tasks | FE5 | FE5: Software Usability Page | FE4,PW2
Frond End Tasks | FE6 | FE6: Usability Problem SubmissionPage | FE5,PW2
Frond End Tasks | FE7 | FE7: Admin Panel | PW5,PW2
Frond End Tasks | FE8 | FE8: Blog Page | PW5,PW2
Frond End Tasks | FE9 | FE9: Software Owner Registartion Page | PW5,PW2
BackEnd Tasks
Back End Tasks | BE1 | BE1:Register Page Integration | PW1, FE1, PW5
Back End Tasks | BE2 | BE2: Login Page Integration | BE1, FE2,PW2
Back End Tasks | BE3 | BE3: List Page Integ. | BE2, FE4,PW2
Back End Tasks | BE4 | BE4: Usability Page Comment Intg. | BE3, FE5,PW2
Back End Tasks | BE5 | BE5: Admin Page Authent. | BE4, FE7,PW2
Back End Tasks | BE6 | BE6: Blog Page Integ. | BE5, FE8,PW2
Back End Tasks | BE7 | BE7: Software Owner Integ. | BE6, FE9,PW2
Back End Tasks | BE8 | BE8: E-mail Notrifies Integ. | BE7,PW2
Back End Tasks | BE9 | BE9: Error Handling | BE1, BE2, BE4, BE5, BE7, PW4, S1, S2, S3,PW2
System Tasks
System Tasks | S1 | Server Settings | -
System Tasks | S2 | Deployment | S1, BE8
System Tasks | S3 | Data Base Integration | S2
Non-Dev | ND1 | Project Management | -
Non-Dev | ND2 | Team Lead (TL) | ND1
Non-Dev | ND3 | Non-Dev Activities | ND1,PW2
QA | ND4 | Planning | ND2,PW2
QA | ND5 | Functional Testing | ND4
QA | ND6 | Regression Testing | ND5
QA | ND7 | Performance Testing | ND6
QA | ND8 | Security Testing | ND7
Non-Dev | ND9 | Bug Fix | ND8

## Test
Project Name: Usibiliy Testing Platform
Website URL: https:
Testing Start Date: -
Testing End Date: -
Test Environment:
Browser: Chrome, Firefox, Edge
| Test Case ID | Test Type | Test Name | Test Description | Input | Expected Output | Actual Output | Severity
| TC1 | Functionality Testing | User Registration - Valid Inputs | Verify that users can successfully register with valid inputs. | Valid username, email, password | User registration successful |  | High
| TC2 | Functionality Testing | User Registration - Invalid Inputs | Verify that users cannot register with invalid inputs. | Invalid username, email, password | Error message displayed |  | Medium
| TC3 | Functionality Testing | User Authentication - Valid Credentials | Verify that users can successfully login with valid credentials. | Registered email, password | User authentication successful |  | High
| TC4 | Functionality Testing | User Authentication - Invalid Credentials | Verify that users cannot login with invalid credentials. | Incorrect email, password | Error message displayed |  | Medium
| TC5 | Functionality Testing | Forgot Password - Email Verification | Verify that users can reset their password via email verification. | Registered email | Password reset email sent |  | High
| TC6 | Functionality Testing | Software Listing - Display Correctly | Verify that the software listing page displays correctly. | N/A | List of software displayed |  | Low
| TC7 | Functionality Testing | Software Usability Page - Display Information | Verify that the software usability page displays correct information. | Selected software | Detailed software information displayed |  | Medium
| TC8 | Functionality Testing | Commenting System - Software Owners | Verify that software owners can comment on findings. | Comment text | Comment added successfully |  | Medium
| TC9 | Functionality Testing | Rating System - Users | Verify that users can rate findings. | Rating value | Rating submitted successfully |  | Low
| TC10 | Functionality Testing | Admin Functions - Usability Problem Review | Verify that admins can review usability problems. | Submitted usability problem | Usability problem reviewed and marked |  | High
| TC11 | Functionality Testing | Admin Functions - Invalid Usability Problem | Verify that admins can mark a usability problem as invalid. | Submitted usability problem | Usability problem marked as invalid |  | Medium
| TC12 | Functionality Testing | Error Pages - Handling | Verify that error pages are displayed correctly. | Trigger error condition | Relevant error message displayed |  | High
| TC13 | Performance Testing | Simultaneous User Handling | Verify that the platform can handle 500 concurrent users. | 500 concurrent users | No performance degradation observed |  | High
| TC14 | Performance Testing | Data Retrieval Optimization | Verify that relevant information is efficiently retrieved. | N/A | Data retrieval optimized |  | High
| TC15 | Performance Testing | Database Caching | Verify that database caching mechanisms are effective. | N/A | Frequently accessed data cached |  | High
| TC16 | Performance Testing | Blog Post Retrieval | Verify that blog posts are retrieved efficiently. | N/A | Blog posts retrieved quickly |  | High
| TC17 | Security Testing | Encryption of Sensitive Data | Verify that sensitive user data is encrypted. | User password | Password encrypted successfully |  | High
| TC18 | Security Testing | Data Transmission Security | Verify that data transmission is secure using HTTPS. | User login credentials | Secure data transmission established |  | High
| TC19 | Security Testing | User Authentication Security | Verify that user authentication mechanism is secure. | User login credentials | Secure user authentication |  | High
| TC20 | Security Testing | Role-Based Access Control | Verify that role-based access control is enforced. | User roles and permissions | Access restricted based on roles |  | High
| TC21 | Usability Testing | User-Friendly Design | Verify that the platform is easy to use with intuitive design. | User navigation | Easy navigation and clear design |  | High
| TC22 | Usability Testing | Pleasant User Experience | Verify that users have a pleasant experience using the platform. | User interaction | Positive user feedback received |  | High
| TC23 | Usability Testing | Efficient Use of Platform | Verify that users can achieve their goals efficiently. | User tasks | Tasks completed efficiently |  | High
| TC24 | Usability Testing | Error Handling | Verify that errors are handled gracefully. | Trigger error condition | Error handled gracefully |  | High